## Cover
Requirements Traceability Matrix (RTM)
Capstone: End-to-End Checkout / Reorder Flow
| Project: | PRT681 Professional Practice – Business Analysis Capstone
| Feature: | Checkout & Reorder Flow for E-Commerce Platform
| Analyst: | Jeffrey Chua Jia Hao
| Date: | 2026-09-29
| Version: | v1.0
📋 Workbook Contents
| Cover | This page – project overview & navigation
| RTM | End-to-end Requirements Traceability Matrix
| NFR & SLA | Non-functional requirements and SLA criteria
| UAT Sign-off | User Acceptance Test sign-off template

## RTM
End-to-End Requirements Traceability Matrix
Req ID | Business Goal | User Story | Acceptance Criteria | Wireframe Screen | Test Scenario ID | Test Scenario Description | NFR / SLA | Priority | Status | Traceability Link
BG-01 | Increase repeat-purchase rate | As a returning user, I want to reorder from order history so that I can save time re-adding items. | Gherkin: Reorder successful (see AC-01) | Order History → Reorder button | TS-01 | Click Reorder: all available items from previous order are added to cart | Latency ≤ 2s under 500 concurrent users | High | Pass | BG-01 → US-01 → TS-01
BG-01 | Increase repeat-purchase rate | As a returning user, I want to reorder from order history so that I can save time re-adding items. | Gherkin: Item out of stock (see AC-02) | Order History → Stock warning modal | TS-02 | Item out of stock: user sees warning and item is excluded from cart | Error rate < 0.1% | High | Pass | BG-01 → US-01 → TS-02
BG-01 | Increase repeat-purchase rate | As a returning user, I want to reorder from order history so that I can save time re-adding items. | Gherkin: Partial stock (see AC-03) | Order History → Cart with adjusted qty | TS-03 | Stock qty < order qty: cart reflects available stock with notification | Latency ≤ 2s | High | Pass | BG-01 → US-01 → TS-03
BG-02 | Reduce checkout abandonment | As a shopper, I want a single-page checkout so that I can complete purchase quickly. | Gherkin: Checkout completion (see AC-04) | Checkout Page → Payment form | TS-04 | Valid payment details submitted: order confirmed, inventory decremented, confirmation email sent | End-to-end latency ≤ 3s | High | Pass | BG-02 → US-02 → TS-04
BG-02 | Reduce checkout abandonment | As a shopper, I want a single-page checkout so that I can complete purchase quickly. | Gherkin: Invalid payment (see AC-05) | Checkout Page → Error banner | TS-05 | Invalid payment: clear error message displayed, no duplicate charges | PCI-DSS compliance | High | Pass | BG-02 → US-02 → TS-05
BG-02 | Reduce checkout abandonment | As a shopper, I want a single-page checkout so that I can complete purchase quickly. | Gherkin: Guest checkout (see AC-06) | Checkout Page → Guest email input | TS-06 | Guest checkout: order confirmed without account creation, email receipt sent | Email delivery ≤ 30s | Medium | Pass | BG-02 → US-02 → TS-06
BG-03 | Ensure data security & compliance | As a business owner, I want all payment data encrypted so that PCI-DSS compliance is maintained. | All card data encrypted at rest (AES-256) and in transit (TLS 1.3) | Architecture diagram → Payment service | TS-07 | Security audit: no plaintext card data in DB, logs, or network traces | PCI-DSS Level 1, OWASP Top 10 | High | Pass | BG-03 → US-03 → TS-07
BG-03 | Ensure data security & compliance | As a business owner, I want all payment data encrypted so that PCI-DSS compliance is maintained. | Gherkin: Session timeout (see AC-07) | Checkout Page → Session expired modal | TS-08 | Session idle > 15 min: user redirected to login, cart preserved | Session timeout 15 min | Medium | Pass | BG-03 → US-03 → TS-08
BG-04 | Support peak-load sales events | As a platform admin, I want the checkout to handle 5,000 concurrent checkouts so that Black-Friday sales don’t crash. | Load test: 5,000 concurrent checkout sessions, 95th percentile latency < 5s | Load-test report → System architecture | TS-09 | Load test passed: CPU < 80%, memory < 85%, zero crashes at 5,000 concurrent | Concurrency 5,000; CPU < 80%; Memory < 85% | High | In Progress | BG-04 → US-04 → TS-09
BG-04 | Support peak-load sales events | As a platform admin, I want the checkout to handle 5,000 concurrent checkouts so that Black-Friday sales don’t crash. | Auto-scaling triggers at 70% CPU utilization | CloudWatch / Monitoring dashboard | TS-10 | Auto-scaling: new instances spin up within 60s of threshold breach | Auto-scale trigger 70% CPU; scale-up ≤ 60s | High | In Progress | BG-04 → US-04 → TS-10

## NFR & SLA
Non-Functional Requirements (NFR) & SLA Criteria
Category | Requirement ID | Criteria | Target / Threshold | Measurement Method | Owner
Performance | PERF-01 | Page load time (checkout) | ≤ 3 seconds (95th percentile) | Lighthouse / New Relic APM | DevOps Team
Performance | PERF-02 | Reorder API response time | ≤ 2 seconds under 500 concurrent | k6 / JMeter load test | Backend Team
Performance | PERF-03 | Auto-scaling trigger | CPU ≥ 70% → scale out within 60s | AWS CloudWatch alarm | DevOps Team
Scalability | SCAL-01 | Concurrent checkout sessions | Support 5,000 concurrent users | Load test: k6, 15-min soak | Platform Team
Scalability | SCAL-02 | Database connection pool | Max 2,000 connections | RDS Performance Insights | DBA Team
Security | SEC-01 | Card data encryption at rest | AES-256 | AWS KMS audit + PCI scan | Security Team
Security | SEC-02 | Data in transit | TLS 1.3 mandatory | SSL Labs scan | Security Team
Security | SEC-03 | Session idle timeout | 15 minutes | Application session config | Backend Team
Security | SEC-04 | OWASP Top 10 coverage | Zero critical/high vulnerabilities | Snyk / SonarQube scan | Security Team
Availability | AVAIL-01 | Uptime SLA | 99.95% monthly uptime | AWS CloudWatch / Statuspage | DevOps Team
Availability | AVAIL-02 | Recovery Time Objective (RTO) | ≤ 30 minutes | Disaster recovery drill | DevOps Team
Availability | AVAIL-03 | Recovery Point Objective (RPO) | ≤ 5 minutes data loss | RDS automated backups + PITR | DBA Team
Reliability | REL-01 | Error rate (5xx) | < 0.1% of all requests | CloudWatch / Sentry | Backend Team
Reliability | REL-02 | Email delivery success rate | ≥ 99.5% | SendGrid / SES analytics | Backend Team
Usability | USAB-01 | Checkout completion rate | ≥ 85% of carts initiated | Google Analytics funnel | Product Team
Usability | USAB-02 | Mobile responsiveness | Pass on iOS Safari + Android Chrome | BrowserStack + manual QA | QA Team

## UAT Sign-off
User Acceptance Test (UAT) Sign-off
| Project Name: | PRT681 Capstone – Checkout & Reorder Flow
| UAT Period: | 2026-09-20 → 2026-09-29
| UAT Environment: | https://uat-checkout.prt681.dev
| Test Lead: | Jeffrey Chua Jia Hao
| Business Stakeholder: | [Name / Role – to be filled]
UAT Execution Summary
| Test ID | Test Scenario | Result | Defects Found | Severity | Sign-off
| TS-01 | Reorder: all items added to cart | Pass | None | – | ✓
| TS-02 | Reorder: out-of-stock warning | Pass | None | – | ✓
| TS-03 | Reorder: partial stock adjustment | Pass | None | – | ✓
| TS-04 | Checkout: successful completion | Pass | None | – | ✓
| TS-05 | Checkout: invalid payment error | Pass | UI-102: error banner spacing | Low | ✓ (with note)
| TS-06 | Checkout: guest checkout | Pass | None | – | ✓
| TS-07 | Security: card data encryption | Pass | None | – | ✓
| TS-08 | Security: session timeout | Pass | None | – | ✓
| TS-09 | Load test: 5,000 concurrent | In Progress | PERF-09: latency 5.2s at peak | Medium | Pending re-test
| TS-10 | Auto-scaling: 60s threshold | In Progress | None | – | Pending re-test
Business Stakeholder Approval
| Signature: ______________________ |  | Date: ______________________
Business Analyst Approval
| Signature: ______________________ |  | Date: ______________________